## Sheet1
goals and objectives
Goal | Supporting Objectives | Delieverables enabling the project objectives | Status
Provide them with a secure and reliable networking architecture with room for future growth | 1.a. Site survey | 1.a.i Inventory and document existing network equipment | Complete
|  | 1.b.i MDF/IDF Locations Identified | Complete
|  | 1.c.i Wireless Access Points identified | Complete
|  | 1.d.i Network Cabling Locations Identifed | Complete
|  | 1.e.i Determine Equipment to be replaced | Complete
| 2.b. Purchase hardware identified for replacement | 2.a.i Generate list of Equipment to purchase | Complete
|  | 2.b.i Sent list of equipment to purchasing department | Complete
| 3.b Establish new networks, Re-IP network devices and create new new DHCP pools | 3.a.i Determine VLANs for department, guests and future phone system and Quality of Service | Complete
|  | 3.b.i Configure equipment VLAN's , QOS and ACLs | Complete
| 4.b Network install and testing | 4.a.i Install new cabling and equipment | Complete
|  | 4.b.i Verify physcial connectity for WAN/WLAN/LAN and VLANS | Complete
|  | 4.c.i Preform ping test between devices to ensure connecivity | Complete
| 5.b Go live | 5.a.i Preform switchover from old to new equipment | Complete
|  | 5.b.i Preform post install connectivity tests with detailed system report | Complete
|  | 5.c.i Return old network equipment to on-site IT Department for disposition | Complete
|  | 5.d.i IT Staff is Trained | Complete